Project Proposal Format

Name of the requesting organisation:	National AIDS Platform

Legal Status of requesting organisation: Registered NGOs

Please enclose a copy of registration certificate (if applicable)

Name of contact person:	John Smith

Position held in the organisation:	Project Coordinator

Contact Address: (Telephone/Fax/E-mail): 7 Eucalyptus Road, 1250 Bluesville

Project Title: 	Fight against HIV/AIDS

Total Project Cost:	                     SCR: 100,000

Funds requested from ERSP	SCR: 80, 000

Project Start Date:	1 January 2006

Project Completion Date:  31 December 2006

## PART A: PROJECT BACKGROUND

# Situation and context:

# Socio-economic and political context and description of specific problem to be addressed. An analysis of the situation which justifies the project.

AIDS remains an incurable disease devastating individuals, communities and nations in the world. Since the start of the epidemic, an estimated 60 million people have been infected with HIV, of whom some 20 million have died (UNAIDS).

Atlantis is one of the countries with the highest prevalence of HIV/AIDS cases. HIV prevalence was 0.1% in the early 1980s and 2 % in the late 1980s. Today, the national HIV prevalence of Atlantis is estimated to be about 16%.  Almost 4 million people are infected and about 2 million children lost their parents by AIDS. Over half of young women aged 20-24 are already infected. The economic costs of AIDS reached 5 % of GDP and are expected to reach 15% of GDP by 2010. If the pandemic continuous unabated, it will have a very negative impact on social, economic and demographic aspects of the society.

Summary of project objectives (intended project outcome):

Briefly describe the project, including what it will aim to achieve and the impact on the problem it seeks to address.

In collaboration with the authorities, the platform will develop a new national AIDS plan that will include capacity building and public awareness aspect with the overall objective of preventing the HIV/AIDS epidemic.

Project Outcome

#### Reducing the spread of AIDS nation-wide

Indicators

Number of new AIDS cases discovered in the country

PART B:  EXPECTED RESULTS

Measurable results (project outputs and indicators):

Provide a summary of the results to be achieved (i.e. outputs), particularly the concrete outputs to be produced and a description of how these results may be measured (i.e. indicators)

| Output | Indicators |
| --- | --- |
| New National AIDS Plan | Extent of distribution of new policies |
|  | Extent of implementation |
| Improved Management and Implementation Capacity for response to HIV/AIDS | Number of new AIDS response units created |
|  | Number of beneficiaries reached |
|  | Number of practitioners and decision-makers trained |
|  | Number and type of stakeholders involved |
| AIDS campaign in line with UNAIDS world AIDS campaign | Number of women/girls, men/boys targeterd by HIV/AIDS prevention awareness |
|  | Extent of press coverage |

Work to be performed (project activities):

Explain the activities to be carried out. Develop a timeframe for each activity (annex 1) & provide an estimated budget (annex 2)

| Output | Activity | Description | Main responsible party* |
| --- | --- | --- | --- |
| New National AIDS Plan | Formation of a multi-stakeholder review committee | Involving NGOs, civil society, persons living with HIV/AIDS, authorities, high-risk groups | National AIDS Platform |
|  | Review of old plan |  | Stakeholder committee |
|  | Development of new plan | Through deliberations and review of existing international documentation | Authorities |
| Improved management and implementation capacity for response to HIV/AIDS | Training | Training workshop for practitioners | National AIDS platform |
|  | Selection process of international experts | They will partake in the development of the training and of the new plan. | National AIDS platform |
|  | Creation of HIV/AIDS specialised units in hospitals | Staffed with trained practitioners and with access to all relevant documentation | Public health authorities |
| AIDS campaign in line with UNAIDS world AIDS campaign | Production of information material | E.g. informative booklets for practitioners and public | National AIDS platform |
|  | Translating material from global campaign into local languages |  | National AIDS platform |
|  | Mobilising media and all relevant stakeholders | Press releases, outreach activities etc. | National AIDS platform |

* In case of projects involving multiple partners

Description of inputs:

Provide a detailed description of the programme/project inputs by activity.  Inputs may include personnel, contracts, equipment, financial contributions and miscellaneous.

| Activity | Inputs |
| --- | --- |
| Formation of a multi-stakeholder review committee | Invitations, key stakeholder identification etc. |
| Review of old plan | International experts, key stakeholders (review committee), written materials |
| Development of new plan | Collaboration between stakeholders and authorities, drafting, distribution, training material development and printouts |
| Training | Catering, translation, administrative coordination, facilities, trainers, trainees |
| Selection process of international experts | Invitations, international experts, transport and accommodation |
| Creation of HIV/AIDS specialised units in hospitals | Facilities, official authorisations, participation by practitioners etc. |
| Production of information material | Design, Contents, Editing, printing, distribution |
| Translating material from global campaign into local languages | Translators, editing, production and distribution |
| Mobilising media and all relevant stakeholders | Press releases, press announcements, invitations, outreach etc. |

### PART C: PROJECT STRATEGY

Organizational capacity:

Demonstrate how the organization has the necessary capacity and experience to achieve the desired results of the project.

The civil society organisations composing the platform have a long history of implementation of AIDS campaigns such as 2003 and 2004 national AIDS campaigns including workshops, press conferences, distribution of educational material.

Partnership strategy:

Describe the strategy that will be used to ensure the success of the project and explain the roles and responsibilities of different partner organisations.

- The National AIDS platform will collaborate with the public health authorities throughout the project, in order to get the appropriate input, access to practitioners, access to data, authorisations, and official support for the new plan.

- Relevant stakeholders and key beneficiaries will be identified and involved in the development of the new plan as well as the training activities. They will represent a cross section of civil society, relevant authorities, people living with HIV/AIDS, at-risk groups, medical practitioners and social workers

- A particular emphasis will be placed on outreach to women and children

- Internationally, this project will be firmly set within the context of UNAIDS’ global AIDS campaign. International experts will be invited to facilitate the training and the development of the new plan.

Advocacy and communications:

How will the project use communications and public education as tools towards achieving results? For example, organisation of public events, publication of news announcements etc.

- The media will be mobilised through invitations to the training, press conferences, press releases etc.

- Information will be widely disseminated to practitioners and people living with HIV/AIDS through social workers, medical practitioners, and with the assistance of civil society organisations.

Sustainability:

Describe approaches and methods for ensuring the sustainability of the project and the possibility for replication or scaling-up.

- The new national AIDS plan will be applied and implemented long after the end of the project, since it will have official endorsement.

- The capacity-building activities (both training and creation of new AIDS units) of the project will ensure the long-term ability of practitioners to deal with the issue, well after this project is over

- The integration within the UNAIDS global campaign will ensure long-term support to the local campaign

Gender Dimension:

Identify women and men needs associated with the project and ensure that women and men are equally involved and benefited from the project.

Women and girls are more vulnerable to HIV/AIDS than men biologically, socially and economically. In Atlantis, due to the current gender relations, women and girls may fail to

protect themselves against unsafe sexual relations. Furthermore, most women and girls lack basic information on how to protect themselves. In most cases, pregnant women suffering from AIDS transmit the virus to their unborn child. To implement this project successfully and reach out the whole population, the following will be pursued:

- Identify and overcome obstacles that limit women’s access to treatment and care, including stigma

- Ensure that data on the epidemic are disaggregated by sex to better understand who is most affected

- Involve women (including women living with HIV/AIDS) at all stages of this project

- Ensure gender equality in implementation of this project.

Annexes:

Attach, as appropriate, job descriptions for consultants, terms of reference for contracts, technical specifications for equipment items, training nomination forms, etc.

Glossary of Key Terms

Impact: Measurable positive and negative long-term effects of the project. These effects can be economic, socio-cultural, institutional, environmental, technological or of other types.

Outcome: The intended or achieved short-term and medium-term effects of project’s outputs, usually requiring the collective efforts of partners.

Outputs: The products and services that result from the completion of the activities

Indicator: A quantitative or qualitative variable that shows verification of changes produced by a project relative to what was planned.

Activity: How the intended outputs will be achieved. Actions taken or work performed through which inputs are mobilised to produce specific outputs.

Inputs: Financial, human, material, technological and information resources that will be used for the activities.

##### Annex 1 - Timeframe

| Annex 1 - Timeframe |
| --- |
| Expected Outputs | Planned Activities List all activities to be undertaken towards stated outputs | Timeframe |
|  |  | 2005/2006 |
|  |  | Qutr1 | Qutr 2 | Qutr 3 | Qutr 4 |  |  |
| New National AIDS Plan | Formation of a multi-stakeholder review committee | X |  |  |  |  |  |
|  | Review of old plan | X |  |  |  |  |  |
|  | Development of new plan |  |  | X |  |  |  |
| Improved Management and Implementation Capacity for response to HIV/AIDS | Training |  |  | X |  |  |  |
|  | Selection process of international experts |  | X |  |  |  |  |
|  | Creation of HIV/AIDS specialised units in hospitals |  |  |  | X |  |  |
| AIDS campaign in line with UNAIDS world AIDS campaign | Production of information material | X |  |  |  |  |  |
|  | Translating material from global campaign into local languages |  | X |  |  |  |  |
|  | Mobilising media and all relevant stakeholders |  | X | X | X |  |  |

| ANNEX II - BUDGET |
| --- |
| Output (administrative use only) | Project Expenses | Cost in SCR | Description | Responsible Party* |
|  | ERSP contribution |
|  | Materials and equipment (if allowed in project criteria) |
|  | Stereliser | 400.00 | For AIDS Unit | National AIDS Platform |
|  | Computers | 606.00 | For AIDS Unit | National AIDS Platform |
| Consumables (e.g. stationary) |
|  | Stationery | 350.00 | For 200 tranees ( flipcharts photocpy ) | National AIDS Platform |
|  | Syringes | 150.00 | For AIDS Unit | National AIDS Platform |
|  | Gloves | 50.00 | For AIDS Unit | National AIDS Platform |
|  | Services (e.g. catering, translation etc.) |
|  | Catering | 500.00 | For training session | National AIDS Platform |
|  | International Expert | 500.00 | 2 Experts for training | National AIDS Platform |
|  | Interpreter | 200.00 | For training session | National AIDS Platform |
|  | Administrative costs (no more than 15% of total) |
|  | Internet & Telephone | 533.00 | For Office administration | National AIDS Platform |
|  | Electricity | 533.00 | For Office administration | National AIDS Platform |
|  | Information activities and publications (e.g. news announcements, public events) |
|  | Production of information matterials | 800.00 | Design, contents, editing printing distribution of 2000 booklets | National AIDS Platform |
|  | Printing | 500.00 | For leaflets | National AIDS Platform |
|  | Announcements | 300.00 | For local newspapers | National AIDS Platform |
|  | Translator / Editor | 200.00 | For 2000 booklets | National AIDS Platform |
|  | Invitations | 100.00 |  | National AIDS Platform |
|  | Miscellaneous (please define precisely) |
|  | Transportation | 569.00 | (Air tickets & Bus service) | National AIDS Platform |
|  | Air ticket | 669.00 | For 2 trainers | National AIDS Platform |
|  | Key Stakeholers meeting expences | 150.00 |  | National AIDS Platform |
|  | Total ERSP expenses | 80,000.00 |  |  |
|  | Organisation contribution | 20,000.00 |  |  |
|  | Total Project Costs | 100,000.00 |  |  |
|  | * For projects with multiple partners |  |